## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-02-c blooteam
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing
Note: | Grayed out stories are not ready for testing.

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MP,10/14 | Pass | MP,11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
Redesigning the structure of our code to make it fit with fundamental design principles. | Our code fits in with good design principles, following the Model View Controller pattern |  |  | Pass | CD, 11/5 |  | N/A | pass | DR, 11/27
As a Player I want to resign so that I can forfeit the game. | Given it is my turn, when I haven't made a move, then I have the option to resign. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given it is my turn, when I have made a move but haven't submitted it, then the option to resign is not available. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given I have the option to resign, when I resign, then I will be taken to the homepage. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given my opponent resigns, when my client updates, then I will see that I have won (my opponent has resigned). |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a player I want to be able to undo a move, so that I can retake the turn. | Given I have just taken a turn, I see a button to undo my previous move, so I can retake it. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20, Change to say "Back up" | pass | DR, 11/27
| Given I click the undo button, my previous move is undone, so I can retake my turn. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a Player I want to make the red player move first so that each game is consistent. | Given I am the red player when I play checkers then I expect to move first. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| No ajax call error on game startup |  |  | Pass | CD, 11/5 |  | N/A | pass | DR, 11/27
As a Player I want to avoid losing all of my checker pieces so that I won’t lose the game. | Given I have no pieces when I start a turn then I will lose the game. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a Player I want to move one checker to an adjacent square diagonally forward so that I make a simple move. | Given valid move when I select a piece then I expect droppable. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20, Make it clearer that you lost | pass | DR, 11/27
| Given invalid move when I select a piece then I expect error message. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a Player I want to make a move each turn so that I will not lose the game. | Given a move when I play checkers then I expect to continue playing. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
| Given no moves when I play checkers then I expect to lose the game. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a Player I want to move one checker by jumping over it diagonally to an adjacent vacant dark square so that I capture an opponent’s piece. | Given a valid jump move when I choose a piece then I expect to capture an opponent's piece and take over the space behind it. |  |  | Pass | CD, 11/5 | Pass | MTG, 11/20 | pass | DR, 11/27
As a Player I want to make a jump move or multiple jump moves if possible so that I don't stop through a multiple jump and abide by the rules. | Given a valid jump move when I play checkers then I expect to do the jump move. |  |  |  |  | pass | MTG, 11/20, Tell the player when they have a jump move they must complete | pass | DR, 11/20
| Given a valid jump move when I just did a jump move then I expect to continue to do jump moves. |  |  |  |  | pass | MTG, 11/20 | pass | DR, 11/20
As a Player I want to make multiple jump moves with one checker to vacant dark squares so that I can capture multiple opponent's pieces. | Given another valid jump move when I previously did a jump move then I expect to be able to jump and capture another opponent's piece. |  |  |  |  | pass | MTG, 11/20 | pass | DR, 11/20
As a Player I want to make a checker reach the row furthest away through a move so that my turn will end and the checker becomes a king. | Given a checker piece when I place said piece on the furthest row away from my side of the board then I expect to change the piece into a king. |  |  |  |  | pass | MTG, 11/20 | pass | DR, 11/20
As a Player I want to make the king checker be able to move diagonally back and forward as far as possible while conforming to the general rules already stated so that I can take advantage of the superior moveset of the king piece. | Given I have a king piece when I move with a king piece then I expect to be allowed to move forward. |  |  |  |  | Fail | MTG, 11/20, King can't move forwards since it can't move backwards in the first place | pass | DR, 11/27
| Given I have a king piece when I move with a king piece then I expect to be allowed to move backwards. |  |  |  |  | Fail | MTG, 11/20, King can't move backwards | pass | DR, 11/27
| Given I have a king piece and a valid forward jump move when I jump move with a king piece then I expect to be allowed to make jump. |  |  |  |  | Fail | MTG, 11/20, King can do nothing | pass | DR, 11/27
| Given I have a king piece and a valid backwards jump move when I jump move with a king piece then I expect to be allowed to make jump. |  |  |  |  | Fail | MTG, 11/20, King can do nothing | pass | DR, 11/27
As a Player I want to look through my game history so that I can see all the matches I have played | Given that a game has ended when I look at my game history then I expect it to be in the list. |  |  |  |  | Fail | MTG, 11/20 | pass | DR, 11/27
As a Player I want to replay a game so that I can see all moves executed in the game. | Given that I am on a Previous Games Page when I click on a game then I expect to go to a Game Page as a viewer. |  |  |  |  | Fail | MTG, 11/20 | pass | DR, 11/27
| Given I was a red player in game I get the red view |  |  |  |  | N/A |  | pass | DR, 11/27
| Given I was a white player in game I get the white view |  |  |  |  | N/A |  | pass | DR, 11/27
| Given I click on Next the game progresses to next move made |  |  |  |  | N/A |  | pass | DR, 11/27
| Given I click on Previous, the game progresses to previous move made |  |  |  |  | N/A |  | pass | DR, 11/27
| Given I click on Exit, I exit the game view page |  |  |  |  | N/A |  | pass | DR, 11/27
As a Player I want to play against AI opponents so that I can practice different strategies. | Given an AI when I am in the lobby and click on it then I expect to play a game with an AI. |  |  |  |  | Fail | MTG, 11/20 | pass | DR, 11/27
| Given I submit turn it's the AI's turn. |  |  |  |  | N/A |  | pass | DR, 11/27
| Given it's the AI's turn it makes and submits a move so it's my turn. |  |  |  |  | N/A |  | pass | DR, 11/27
| Given I have no pieces when I start a turn then I will lose the game. |  |  |  |  | N/A |  | pass | DR, 11/27
| Given AI has no pieces left when it's its turn I win the game |  |  |  |  | N/A |  | pass | DR, 11/27